## 2018-19 Audit
| Audit Finding | Reference to Dr.J's Excerpt | Repeat from PY | Status | Status Update | Corresponding Finding from 2020 Audit Report
1 | 2019-001 Closing Process and Control Environment | Table A 2019-001 | yes Item 2018-01 | Implemented | Implemented district close schedule; Edgerock contracted to design and support with implementation of monthly close | Finding 2019-001 Closing Process and Control Environment
2 | 2019-002 Capital Assets | Table A 2019-002 | yes Item 2018-02 | In progress | In progress: District is currently engeged with Oracle to design asset managment module in Peoplesoft (to go live by September 2021) | Finding 2019-002 Capital Assets (1)
Finding 2019-002 Capital Assets (2)
3 | 2019-003 Internal Service Fund deficit Fund Balance | Table A 2019-003 | no | Implemented | Corrective action was taken | Finding 2019-003 Internal Service Fund Deficit and Fund Balance
4 | 2019-004 Vacation Accrual | Table A 2019-004 | no | Implemented | Implemented- policy update needed: 1. Admn- policy should address employees that exceeded the cap prior to implementation 2. Policy should be implemented for non-Administrators | Finding 2019-004 Vacation Accural
5 | 2019-005 Return to Title IV Program | Table A 2019-005 | yes Item 2018-03 | In progress | Plan with Edgerock to improve financial aid administration | Finding 2019-005 Special Tests and Provision: Return to Title IV (1)
Finding 2019-005 Special Tests and Provision: Return to Title IV (2)
6 | 2019-006 Direct Loan Reconciliation | Table A 2019-006 | no | In progress | Corrective action was taken | Finding 2019-006 Special Tests and Provision: Direct Loan Reconciliation
7 | 2019-007 Special Tests and Provisions: COD Reporting 2020-007 Internal Controls Over Federal Awards | Table A 2019-007 | yes Item 2018-04 | In progress | Plan with Edgerock to improve financial aid administration | Finding 2019-007 Common Origination and Disbursement (COD) Reporting
8 | 2019-008 444-Apprenticeship Related and Supplemental Instruction (RSI) Funds | Table A 2019-008 | yes Item 2018-05 | Implemented | Corrective action was taken | Finding 2019-008 444 Apprenticeship Related and Supplemental Instruction (RSI) Funds
9 | 2019-009 425-Residency Determination for Credit Courses | Table A 2019-009 | no | Implemented | Corrective action was taken | Finding 2019-009 425 Residency Determination for Credit Courses (1)
Finding 2019-009 425 Residency Determination for Credit Courses (2)
10 | 2019-010 491- Education Protection Account Funds | Table A 2019-0010 | no | Implemented | Corrective action was taken | Finding 2019-010 Education Protection Account Funds
Corrective action was taken
Corrective action was taken

## 2019-20 Audit
| 2020 Audit Results and Corrective Action Plans |  |  |  |  | Financial Aid Policies and Prcedures | **Note: The 2020 audit engagement ended in February 26, 2021; the 2021 audit kicked off in May which results in the probability for repeat findings given the limited time for any implementation of corrective action to reflect in audit pool for 2021.
| Audit Finding Report | Auditor's Recommendation | Proposed Action | Correction Implementation | Repeat from PY | Status Update | Corresponding Finding from 2020 Audit Report
1 | 2020-001 Closing Process and Control Environment | Recommendation: We believe that a review and evaluation of transactions and proper closing procedures would expedite the year-end closing process and provide for more accurate results. Documentation may include policy manuals, process models, flowcharts, job descriptions, documents, and forms, and can be in paper form, electronic files, or other media. In addition, the documentation can be used in reinforcing established policies and procedures, evaluating performance, or training a new employee to perform the process. | Action taken in response to finding: PCCD will improve existing year end closing process (including a checklist and timeline) and will also implement a monthly close to ensure reconciliation and adjustments are made in a timely and accurate manner. Assessment of duties among staff will be conducted so that assigned responsibilities are completed accordingly. The District will provide year end closing documentation from prior year and update with new information for the current year. The District will deploy concentrated efforts to resolve prior year receivables. Staff training will be implemented to promote improved capacity and controls. The District is exploring options to manage and report student receivables. | The District is currently implementing a monthly close process that will support improved accounting practices districtwide | yes Item 2019-001 | Completion was estimated at April 2021. Edgerock Technologies was contracted to support this work. The project continues as issues are being worked out with scripts for posting and report details. Update has been requested from Edgerock. End goal:1) Closing schedule, 2) functioning PeopleSoft module to close periods, 3)documentation, 4) training, 5) districtwide communication, and 6) support to College Business Managers | Finding 2020-001 Closing Process and Control Environment | Will request calendared meetings from the work group/IT
2 | 2020-002 Capital Assets | Recommendation: We recommend the district evaluate capital assets reconciliation process to ensure all transaction are properly recorded and reviewed in a timely basis. | Action taken in response to finding: The recent upgrade (February 16, 2021) to PeopleSoft will allow the District to accurately identify and manage construction projects. Coordinators will then be able to track status of projects and reconcile accordingly. Existing process will be enforced to identify completion via required documentation. | Peralta is currently engaged with PeopleSoft in the launch of several Finance modules (Expense Management, Asset Management, and Contract Management). The project is 70% complete and is in its final phase of testing enhanced utilities to accommodate the fixed assets module. | yes Item 2019-002 | Phase I - system upgrade completed Phase II - PeopleSoft module execution (est. tbd) The Chancellor has convened a Steering Committee comprised of IT, Finance, HR and PeopleSoft to assess progress and project timelines. These discussions will be enriched by an external assessment of the project to be completed over the next month to ensure the district has covered all basis for a successful transition to full utilization of the new modules. To allow for any necessary modifications, extensive staff training and development of training materials, all modules are expected to go live no later than November 2021. End goal: complete implementation of districtwide purchasing, tracking, monitoring and depreciation management. Proper accounting of assets from frontend user to backend reporting of depreciation; encompassing accurate coding for various areas: Procurement/Warehouse/Fiscal Services. | Finding 2020-002 Capital Assets | Will request notes from Royl and calendared meetings from IT
3 | 2020-003 Vacation Accrual | Recommendation: The District should develop and implement appropriate policies and procedures to monitor employee vacation accruals and cease the accrual when maximum hour limit is reached. Until the employees uses vacation hours, vacation hours should not continue to accrue. The District should encourage employees to utilize vacation hours they have accrued to help reduce the liability. | Action taken in response to finding: In 2020, the District implemented a cap on vacation accrual of 44 days for management and administrators. This policy did not include classified staff; no cap was implemented. Balances for management vacation accrual prior to 2020 were not impacted. The District plans to enforce vacation usage for all other employees not covered by a cap policy. | Management and uniion discussion needed to strategically plan how to implement and enforce a cap on vacation accrual. | yes Item 2019-004 | A policy cap was established in fall 2020 to limit vacation accrual to 374 Administrators. Auditors responded that there was no verbiage included to cover those employees who were already over the newly initiated cap. Auditors also encouraged a cap for all employees - this is a contractual item for labor groups and will be addressed for all unions during reopeners over the next year when the contracts sunset. | Finding 2020-003 Vacation Accrual | Will request a copy of the communication sent by prior Chancellor
4 | 2020-004 Student Financial Assistance Cluster – Special Tests and Provisions: Enrollment and Certification Approval Report | Recommendation: We recommend the Colleges’ establish procedures to ensure the timely reporting of ECAR changes to the Department of Education. | Action taken in response to finding: Oversight of financial aid has shifted to the VC of Administration and Finance as of fall 2020, after being under the VC Academic Affairs and Student Services for the prior two years. The District will work with the college presidents, vice presidents to implement a process for updating Department of Education of new Financial Aid staff representatives within the 10-day requirement. | 1) Improved communication with campus units, 2) "Role Information" for new hires in critical positions within the Financial Assistance Clusters to accompany training. | no | Implemented; policy created | Finding 2020-004 Student Financial Assistance Cluster- Special Tests and Provision: Enrollment and Ceritifcation Approval Report
5 | 2020-005 Special Tests and Provisions: COD Reporting | Recommendation: We recommend the Colleges’ evaluate their procedures and policies around reporting Pell and Direct Loan disbursements to COD to ensure that student information is reported accurately and timely. | Action taken in response to finding: Oversight of financial aid has shifted to the VC of Administration and Finance as of fall 2020, after being under the VC Academic Affairs and Student Services for the prior two years. The District will work with the college presidents, vice presidents to reinforce the process implemented in FY20 to report the COD and drawdown on a weekly basis. The District has experienced continued voids in critical roles and has recently hired 2 Financial Aid Directors at the colleges; two vacancies currently exist. | The District began regular meetings with campus financial aid leaders, increased training opportunities and outline of clear expectations to address compliance, accuracy and timeliness of reporting. | yes Item 2019-007 | Plan with Edgerock to Improve Financial Aid Administration | Finding 2020-005 Special Tests and Provisions: COD Reporting
6 | 2020-006 Gramm-Leach Bliley Act | Recommendation: We recommend that the District engage a third party to perform the risk assessment to address the areas required by the Gramm-Leach-Bliley Act and ensure that there are documented safeguards for identified risks. Explanation of disagreement with audit finding: There is no disagreement with the audit finding. | Action taken in response to finding: Due to COVID the risk assessment was not performed during its usual time as IT was heavily involved with a systemwide upgrade which will utilize PeopleSoft Cloud Security going forward. Documentation of OCI security overview will be provided. | Connect w/ Antione | no | Implemented - February 2021 w/ Peoplesoft upgrade. Additionally Finance and IT are currently working with CLA auditors to identify a risk assessment tool/resources that can be used to satisfy this finding. Second follow up meeting to be scheduled in the next week. | Finding 2020-006 Gramm-Leach Bliliy Act
7 | 2020-007 Internal Controls Over Federal Awards | Recommendation: We recommend that the Colleges’ reinforce their control structure and control environment to ensure there is an appropriate tone at the top of the organization, to monitor proper follow-up on audit findings and review all activity level controls to ensure compliance with the various requirements of the Student Financial Assistance Cluster. | Action taken in response to finding: Oversight of financial aid has shifted to the VC of Administration and Finance as of fall 2020, after being under the VC Academic Affairs and Student Services for the prior two years. The District will work with the college presidents, vice presidents to review practices, reporting expectations, and ensure the separation of duties. | The District began regular meetings with campus financial aid leaders, increased training opportunities and outline of clear expectations to address compliance, accuracy and timeliness of reporting. | no | Plan with Edgerock to Improve Financial Aid Administration | Finding 2020-007 Internal Controls Over Federal Awards
8 | 2020-008 Special Tests and Provisions: Enrollment Reporting | Recommendation: We recommend the District review its reporting procedures to ensure that enrollment and program information is accurately reported to National Student Loan Data System (NSLDS) as required by regulation. | Action taken in response to finding: Oversight of financial aid has shifted to the VC of Administration and Finance as of fall 2020, after being under the VC Academic Affairs and Student Services for the prior two years. The District will work with the college presidents, vice presidents to review reporting procedures with colleges to ensure enrollment and program date information is accurately reported to NSLDS as required. College Business Services will be included in this process. | The District began regular meetings with campus financial aid leaders, increased training opportunities and outline of clear expectations to address compliance, accuracy and timeliness of reporting. | no | Implemented among college offices, weekly meetings with campus financial aid leadership. Utilizing Edgerock for process improvement throughout financial aid processes. Daily meetings with Edgerock are held to address manual, combersome, outdated and inefficient processes. Documentation and training to follow improvements and automated processes. Issues with repackaging adjustments are part of agenda items for | Finding 2020-008 Special Tests and Provisions: Enrollment Reporting
9 | 2020-009 Outstanding Student Refund Checks | Recommendation: We recommend the District review its procedures related to outstanding student refund checks to ensure they are being returned to the Department of Education or disbursed to students as stated in the criteria mentioned above. | Action taken in response to finding: Oversight of financial aid has shifted to the VC of Administration and Finance as of fall 2020, after being under the VC Academic Affairs and Student Services for the prior two years. The District will review its procedures to ensure that staff is trained to return funds to the Department of Education if payment to student is unsuccessful within a 30-day window. | The District began regular meetings with campus financial aid and business leaders, increased training opportunities and outline of clear expectations to address compliance, accuracy and timeliness of reporting.The District to implement policies to ensure that funds be returned for all unsuccessful student payments within set timeframe (30 days). Campus Business Officers to be involved in the outreach efforts to get funds to students prior to return via COD. | no | Implemented among district/college offices - currently manual communication effort. Currently working with IT support to automate communication to campus offices in support of speed and accuracy. | Finding 2020-009 Outstanding Student Refund Checks | Following up with it to get automated notices sent to students whose refunds are returned from Bank Mobile
10 | 2020-010 Activities Allowed or Unallowed, Allowable Cost/Cost Principles and Period of Performance | Recommendation: We recommend management maintain adequate documentation to support all charges to new and existing federal programs. | Action taken in response to finding: The District will make an adjustment to move the questionable amounts $378,498 and $430,445 (total $808,943) from CRF Block Grant back to General Fund and reclassify with allowable laptop costs previously incurred by Measure G funds. A copy of the journal will be provided, and an updated satisfactory report will be filed with the state for Cycle 4. | A Journal was submitted to reclassify initial expenditures charged to the CRF funds and replace with allowable expenses supporting laptop purchases for remote instruction,. | no | This was corrected by a one time journal for a one-time expense. The initial expense was found to be unallowable. The District corrected the entry by journaling out the expenses for nursing program and transportation and journaling in a portion of the expenses inccured by the Bond funds that were used for emergency lap top purchases. The grant of $808K has been expensed and final reporting has been completed. | Finding 2020-010 Activities Allowed or Unallowed, Allowable Cost/Cost Principles and Period of Performance | 3.11.21 Will update with journal and final CRF report.
Implemented: utilizing Edgerock for process improvement in this area. Daily meetings with Edgerock and weekly meetings with campus financial aid leadership are held to address manual, combersome, outdated and inefficient processes. Documentation and training to follow improvements and automated processes.
Implemented: utilizing Edgerock for process improvement in this area. Daily meetings with Edgerock and weekly meetings with campus financial aid leadership are held to address manual, combersome, outdated and inefficient processes. Documentation and training to follow improvements and automated processes.